Background Document for UNDG Meeting 
24th September 2008

Agenda item # 3

Matters arising from last meetings

In response to the requests from Delivering as One Pilots, and/or UNCTs

UNDG 2008 Prioritized Workplan

| Working Group on Country Office Business Operation Issues |
| --- |
| Issue | Priority | Deliverables | Timeframe | Lead Responsibility |
| Common Services and Procurement | Implementation of common services, including joint procurement, at country level reinforced | Common services and procurement issues raised by ‘Delivering as One’ pilots analyzed and solutions proposed | Oct 2008 | TT on Common Service & Procurement Lead – UNDP |
| Common Premises | Guidance and support to Country Teams establishing common premises provided | Guidance note on financing options for UNCTs to cover common premises costs developed | Oct 2008 | TT on Common Premises Lead – UNICEF |
| Human Resources | Areas for further harmonization of Human Resources policies and procedures identified through analysis and support on setting up joint teams in ‘Delivering as One’ countries | Guidance to Viet Nam on setting up One Communications Team provided Further HR issues in pilot countries identified and guidance/support for their implementation provided or in process | Nov 2008 Nov 2008 | TT on Human Resources |
| Information Communication Technology (ICT) | ICT solutions for increased inter-agency collaboration developed and piloted in ‘Delivering as One’ countries | Recommendations for a common domain name for all ‘Delivering as One’ countries in collaboration with ICT Network developed | Nov 2008 | ICT Task Team |
|  |  | Blueprints for possible inter-linkages of agencies’ networks (with support structures to be defined by UNCTs) in selected pilot countries developed | Nov 2008 | Lead – WFP |
| HACT | Progress on the implementation of HACT based on existing accountability mechanisms (UNCTs and RMTs) reviewed and its implementation by non-Excom agencies supported | HACT is adopted by the Specialized Agencies for the pilot countries including clear timelines for implementation | Sep 2008 | HACT Advisory Committee Lead – UNFPA |
| Working Group on Joint Funding, Financial and Audit Issues |
| Issue | Priority | Deliverables | Timeframe | Lead Responsibility |
| Joint Funding | Management and oversight of MDTFs and One Funds enhanced | Guidance note on establishing and managing MDTFs and a protocol on the role of the AA developed Effective corporate oversight mechanism linked to MDTF fiduciary management oversight framework established | Sep 2008 Nov 2008 | TT on Joint Funding Lead - UNAIDS |
| Financial Issues | Financial issues from the DaO countries addressed | A harmonized definition of savings arising from reductions in transaction and support costs and the policy on deployment of such savings developed | Nov 2008 | TT on Financial Issues Lead – UNFPA |
|  |  | Harmonization issues from DaO countries in particular relating to financial policies and procedures addressed | Nov 2008 |  |
| Working Group on RC System Issues |
| Issue | Priority | Deliverables | Timeframe | Lead Responsibility |
| RC/UNCT Working Relations | RCs and UNCTs roles clarified | RC Job Description revised Guidelines on Working Relations for UNCTs developed Dispute Resolution Mechanism adopted | Oct 2008 Oct 2008 Oct 2008 | UNICEF (as Chair of WG) UNICEF (as Chair of WG) WHO/UNDP |
| RC/HC Talent Management Initiative | RC/HC candidate pool enlarged | Implementation plan to build a viable pool of RC/HC available candidates prepared and initiated | Dec 2008 | UN-OHRM (as Chair of the Talent Management Task Force) |
| RC/UNCT Performance Appraisal System | RC/UNCT performance appraisal system strengthened | Second generation of the 180 degree tool for RC and UNCT competency assessment and development produced, with pilot implementation by the end of 2008 | Dec 2008 | Task Force on the 180 tool |
| RC/UNCT orientation and training | First time RCs are fully briefed and trained | Integrated orientation programme for RCs designed and delivered, with increased interaction across UN agencies and inclusive of political skills and acumen | Nov 2008 | UN System Staff College |
| Working Group on Programming Issues |
| Issue | Priority | Deliverables | Timeframe | Lead Responsibility |
| Capacity Development | Integration of capacity development in programming deepened | Stocktaking of networks and knowledge spaces conducted and training module on UNDG approach to supporting capacity development produced | Dec 2008 | UNDP, FAO, OHCHR |
| Normative-Operational linkages | Linkages between normative work and operational activities and the integration of key principles and thematic issues strengthened | Case studies on climate change action by UNCTs produced | Dec 2008 | UNEP-UNDP/UNICEF, UNOPS |
| System-wide coherance | Improvement of system-wide coherance at country level programming ensured | CCA/UNDAF guidelines updated in light of lessons learned from DaO pilots and 2007 UNDAF roll-out countries Brief overview of lessons learned and good practices of UNCTs experiences, as well as identification of issues for further work on simplifying the Common Country Programming Process produced | Dec 2008 Dec 2008 | UNICEF UNICEF/UNESCO |
| Accountability for results | Accountability for results and monitoring and evaluation systems for UNCT use strengthened | Action Plan to address systemic RBM issues developed and implementation initiated in 2008 UNDAF M&E guidance updated | Dec 2008 Oct 2008 | UNFPA-UNICEF/UNIFEM, UNDP |
| Aid Effectiveness | Agreed commitments on aid effectiveness implemented | Unified presence and position of the UN system at Accra and Doha HL meetings ensured | Dec 2008 | UNDP-UNICEF |
|  |  | Operational guidance on aid modalities, effectiveness and alignment developed | Dec 2008 | UNDP-UNFPA |
| UNDG-ECHA Working Group on Transition Issues |
| Issue | Priority | Deliverables | Timeframe | Lead Responsibility |
| RC/HCs, RCOs and UNCTs in countries in transition | RCs and UNCTs in transition countries are supported on a predictable and sustainable basis to ensure proper planning and coordination capacity | Clarification note to UNCTs on the different transition planning processes produced Guidance note on approaches to addressing Transitional Financing and establishing/participating in MDTFs developed Communication tools to inform UNCTs of the different tools and support available for transition countries developed | Dec 2008 Dec 2008 Dec 2008 | CPC/DOCO CPC/DOCO CPC/DOCO |
| Strengthened Partnerships | Cooperation with inter-agency fora and Secretariat bodies towards integrated planning and operations strengthened | Tools and guidance to enhance cooperation with CWGER developed Tools and guidance to enhance cooperation with Framework Team identified | Dec 2008 Dec 2008 | CPC/DOCO CPC/DOCO |
| Collaboration with the World Bank | Inter-operability between UN actors and between UN actors and the WB towards a more efficient use of resources enhanced | PCNA toolkit review finalized Input to the development of a Post-Disaster Needs Assessment (PDNA) methodology provided UN/WB partnership note and fiduciary agreement finalized Partnership note between WB-EC-UN on PDNA and PCNA finalized | Dec 2008 Dec 2008 Oct 2008 Oct 2008 | CPC/DOCO CPC/DOCO CPC/DOCO CPC/DOCO |
| Resources for transition | Availability of resources to transition countries, in particular at the early stages of recovery increased | Advocacy strategy to foster donor attention and resources to transition developed Outreach strategy on transition requirements developed | Dec 2008 Dec 2008 | CPC/DOCO CPC/DOCO |

# Footnotes

The Change Management Task Team is working with the pilot countries on a set of country identified deliverables.